## Sheet1
KROWOR MUNICIPAL ASSEMBLY
2025 COMPOSITE ANNUAL ACTION PLAN FROM THE MTDP 2022-2025
| Programme Based Budget (PBB) | Sub Programme | Broad Activities | Location | Time Frame |  |  |  | Cost |  |  | Programme Status |  | Implementation Agency/Institution
[5 empty] | Q1 | Q2 | Q3 | Q4 | GOG | IFG/ | Others | New | On-Going | Lead | Collaborators
ABFA
1 | Infrastructure Delivery & Management | Urban Roads and Transport Services | Undertake desilting of drains in some selected areas in Nungua | Nungua |  | x | x |  | 100000 | IGF |  |  | x | DUR | PHYSICAL PLANNING AND WORKS
2 | Infrastructure Delivery & Management | Urban Roads and Transport Services | Undertake patching of potholes on selected roads | Municipal wide | x | x | x | x | 180000 | IGF |  |  | x | DUR | PHYSICAL PLANNING AND WORKS
3 | Infrastructure Delivery & Management | Urban Roads and Transport Services | Gravelling of selected roads within Krowor municipality(650m) | Municipal wide | x | x | x | x | 160000 | IGF |  |  | x | DUR | PHYSICAL PLANNING AND WORKS
4 | Infrastructure Delivery & Management | Urban Roads and Transport Services | Minor drainage repair and kerb works on selected locations | Municipal wide | x | x | x | x | 80,000.00 | IGF |  |  | x | DUR | PHYSICAL PLANNING AND WORKS
5 | Infrastructure Delivery & Management | Urban Roads and Transport Services | Construction of 0.9 U-drains,0.6 U-drain,0.9 U-drain and 1.2 rectangular drain within Krowor municipality | Municipal-wide | x | x | x | x | 250,000.00 |  |  |  | x | DUR | PHYSICAL PLANNING AND WORKS
6 | Infrastructure Delivery & Management | Urban Roads and Transport Services | Undertake traffic and safety management activities within Krowor municipality |  | x | x | x | x |  | 50000 |  |  |  | DUR | PHYSICAL PLANNING AND WORKS
7 | Infrastructure Delivery & Management | Urban Roads and Transport Services | Undertake dredging works | Municipality wide | x | x | x | x |  | 1500000 |  |  |  | DUR | PHYSICAL PLANNING AND WORKS
8 | Infrastructure Delivery & Management | Urban Roads and Transport Services | Undertake project Site supervision | Municipality wide | [5 empty] | 2500 |  |  |  | DUR | PHYSICAL PLANNING AND WORKS
9 | Infrastructure and Development | Spatial Planning | Organize Technical sub-committee inspection and meetings, Spatial Planning and SAT meetings | Municipal Assembly | x | x | x | x | 88000 | IGF |  |  | x | PPD | EPA, LANDS COMMISSION, WORKS DEPT., URBAN ROADS
10 | Infrastructure and Development | Spatial Planning | Prepare and update local Plans/Schemes | Municipal Assembly | x | x | x | x | 36,00.00 | IGF |  |  | x | PPD | EPA, LANDS COMMISSION, WORKS DEPT., URBAN ROADS
11 | Infrastructure and Development | Spatial Planning | Organise sensitisation on permitting process and regularization of development without permit | Municipal Assembly | x | x | x | x | 18000 |  |  |  |  | PPD | WORKS DEPT.
12 | Infrastructure and Development | Spatial Planning | Undertake Street Naming and Property Addressing Public consultation, ground trothing and procurement /installation of street signage | Municipal wide | x | x | x | x | 65000 | IGF |  |  | x | PPD | INFORMATION DEPT.
13 | Infrastructure Delivery & Management | Public Works, Rural Housing and Water Management | Renovation and Maintenance of public schools | Nungua |  | x | x | x | 26879.5 |  |  |  | x | Works | Education dept.
14 | Infrastructure Delivery & Management | Public Works, Rural Housing and Water Management | Construction of 2-storey 6-unit classroom block at Islamic primary school Nungua Zongo | Nungua | x | x | x | x | 835,502,38 |  |  | x |  | Works | Education Dept.
15 | Infrastructure Delivery & Management | Public Works, Rural Housing and Water Management | Construction of 2-storey 12 unit class room block with ancillary facilities at Nungua St. Augustines Anglican School | Nungua | x | x | x | x | 680584.12 |  |  |  | x | Works | Education Dept.
16 | Infrastructure Delivery & Management | Public Works, Rural Housing and Water Management | Construction of 2-storey 6-unit class room block with ancillary facilities at Nungua Cluster of schools | Nungua | x | x | x | x | 100000 |  |  | X |  | Works | Education Dept.
17 | Infrastructure Delivery & Management | Public Works, Rural Housing and Water Management | Undertake installation and maintenance of streetlight in some selected electoral areas | Selected areas | x | x | x | x |  | 80000 |  | X |  | Works
18 | Infrastructure Delivery & Management | Public Works, Rural Housing and Water Management | Construction and completion of existing lekma Polyclinic (phase 2) | Nungua Adogono | x | x | x | x | 870000.4 |  |  |  | X | Works | Health directorate
19 | Infrastructure Delivery & Management | Public Works, Rural Housing and Water Management | Undertake inspection and field operations | Municipal wide | x | x | x | x |  | 30000 |  |  |  | Works | Development Planning Unit
20 | Infrastructure Delivery & Management | Public Works, Rural Housing and Water Management | Construction of 2-storey 6-unit class room block with anaciliary facilities at Nungua St. Peters Anglican Basic school. | Sookpoti | x | x | x | x | 100000 | 1500000 |  | x |  | Works | Development Planning Unit
21 | Infrastructure Delivery & Management | Public Works, Rural Housing and Water Management | Fabrication and supply of school Furniture | Some selected schools | x | x | x | x | 560000 |  |  | x |  | Works | Education dept.
22 | Environmental Management | WASTE MANAGEMENT | Undertake evacuation of refuse heaps | MUKWEJOR, SOOKPOTI | x | x | x | x |  | 20000 |  |  | x | EHU | WASTE
23 | Environmental Management | Environmental Health and Sanitation Services | Undertake regular and periodic premises inspection. | NUNGUA | x | x | x | x |  | 9000 |  |  | x | EHU | GHANA HEALTH SERVICE
24 | Environmental Management | Environmental Health and Sanitation Services | Undertake updating on gazetting of DESSAP and Sanitation by- laws | Assembly | x | x | x | x |  | 10000 |  |  | x | EHU | PLANNING
25 | Environmental Management | Waste Management | Organize National Sanitation Day Programme | Municipal wide | x | x | x | x |  | 30000 |  |  | x | EHU | WASTE SERVICE PROVIDERS
26 | Environmental Management | Environmental Health and Sanitation Services | Undertake monitoring and supervision of Household and Public toilets | Municipal wide | x | x | x | x | 5000 |  |  |  | x | EHU | WASTE SERVICE PROVIDERS
27 | Environmental Management | Environmental Health and Sanitation Services | Organize sensitization programs on food and personal hygiene | Municipal wide | x | x | x | x |  | 5000 |  |  | x | EHU | GHANA HEALTH SERVICE
28 | Environmental Management | Environmental Health and Sanitation Services | Organize education for 30 schools on environmental hygiene / school health education | Municipal wide |  | x | x |  |  | 5000 |  |  | x | EHU | GHANA EDUCATION SERVICE
29 | Environmental Management | Environmental Health and Sanitation Services | Undertake burial of paupers and management of cemetries |  | x | x | x | x | 2500 |  |  |  |  | EHU | GHS
30 | Environmental Management | Environmental Health and Sanitation Services | Undertake fumigation/derating of schools, Poly clinics CHPS compound Library market etc | [6 empty] | 15000 |  |  |  | EHU | Zoomlion Ghana Limmited
31 | Environmental Management | Environmental Health and Sanitation Services | Organize environmental enhancement programme | Municipal |  |  |  |  | 12000 |  |  |  |  | EHU | NADMO
32 | Environment & Sanitation | Disaster Prevention and Management | undertake awareness on disaster prevention through public education | Municipal wide | x | x | x | x | 35000 | IGF |  |  | x | NADMO | GNFS, EHU, GES, GHS
33 | Environment & Sanitation | Disaster Prevention and Management | Undertake tree planting exercise to Reduce Risk and vulnerability and promote climate change risk management | Municipal wide | X |  |  | X | 37000 | IGF |  |  | X | NADMO | AGRIC, URBAN ROADS, EHU,
34 | Environment & Sanitation | Disaster Prevention and Management | Resettle and rehabilitate disaster victims, train, form and provide livelihood for DVGs | Municipal-wide | X | X | X | X | 42000 | DACF |  |  | X | NADMO | NADMO REGIONAL OFFICE,
35 | Environment & Sanitation | Disaster Prevention and Management | Undertake Field Trips and holding meetings in disaster prone areas | Municipal Wide | X |  |  | X | 5000 | IGF |  |  | X | NADMO | WORKS DEPT., URBAN ROADS DEPT., EHD
36 | Environment & Sanitation | Disaster Prevention and Management | Organize Simulation Exercises for Staff and other Stakeholders. | Municipal Wide |  | X | X |  | 10000 | IGF |  | X |  | NADMO | 48 ENGINEERS
37 | Environment & Sanitation | Disaster Prevention and Management | Training workshop organized for staff and stakeholders to improve knowledge on new disaster trend. | Municipal Wide | X |  |  | X | 15000 | IGF |  |  |  | NADMO | ADMIN
38 | Environmental Management | Natural Resource and conservation management | Sensitize 60 fishermen on IUU fishing | Nungua |  |  | x |  | 2000 | IGF |  |  | x | Fisheries | NATURAL RESOURCE AND CONSERVATION AND FISHERIES
39 | Environmental Management | Natural Resource and conservation management | Train 60 fishermen on livelihood support programs like livestock rearing , fish farming etc. | Nungua |  | x |  |  | 3000 | IGF |  |  | x | Fisheries | NATURAL RESOURCE AND CONSERVATION AND FISHERIES.
40 | Environmental Management | Natural Resource and conservation management | Train 60 fish processors on record keeping and good business management | Nungua |  |  | x |  | 2000 | IGF |  |  | x | Fisheries | NATURAL RESOURCE AND CONSERVATION AND FISHERIES.
41 | Environmental Management | Natural Resource and conservation management | Conduct fish processors survey | Nungua |  | x |  |  | 3000 | IGF |  |  | x | Fisheries | NATURAL RESOURCE AND CONSERVATION AND FISHERIES.
42 | Environmental Management | Natural Resource and conservation management | Organise Clean up at the ebach and Train 60 fishermen on good environmental practices and effects of plastic and on aquatic life | Nungua |  |  | x |  | 3000 | IGF |  |  | x | Fisheries | NATURAL RESOURCE AND CONSERVATION AND FISHERIES.
43 | Management & Administration | Legislative Oversights | Organise Statutory meetings | Municipal Assembly | x | x | x | x |  | 100000 |  |  | x | ADMIN | HR
44 | Management & Administration | General Administration | Support Nungua traditional council during the Kpledjoo (Homowo) festival in June | Nungua |  |  | x |  |  | 40000 |  |  | x | ADMIN | CULTURE
45 | Management & Administration | General Administration | Organize statutory meetings( Committee and general council meetings | Krowor North Zone | x | x | x |  |  | 20340 |  |  |  | KN/ KS | Central Admin
46 | Management & Administration | General Administration | Revenue mobilization from self employed Artisan | Krowor North Zone | [9 empty] | KN/ KS | Central Admin
47 | Management & Administration | General Administration | Organize health sensitization programs | Krowor North Zone | [5 empty] | 25000 |  |  |  | KN/KS | Central Admin
48 | Management & Administration | General Administration | Organize Quarterly General Council meetings | Krowor South Zone | x |  | x | x |  | 20340 |  |  |  | KS | Central Admin
49 | Management & Administration | General Administration | Construction of 2n. room urinal with 1800 liters polytanks connected to Ghana Water Company | Krowor South Zone | x | x | x | x |  | 30000 |  |  |  | KS | Central Admin
50 | Management & Administration | Human Resource Management | Preparation & implementation of Capacity Building Plan for 2025 | [5 empty] | 30900 | 50000 |  |  |  | HR | All Dept.
51 | Management & Administration | Human Resource Management | Co-ordinate the Implementation of Performance Management System/Staff Appraisal and Performance Contract between Hon. MCE & MCD | Municipal Assembly | x | x | x | x |  | 12000 |  |  | x | HR | ALL DEPARTMENTS
52 | Management & Administration | Human Resource Management | Input/Update Human Resource Management Information System (HRMIS) | Municipal Assembly | x | x | x | x |  | 24000 |  |  | x | HR | ADMIN
53 | Management & Administration | Human Resource Management | Organize 2 No Staff Durbar | Municipal Assembly |  | x | x |  |  | 15000 |  |  | x | HR | ADMIN
54 | Management & Administration | Human Resource Management | Undertake 2 staff Audit & Monitoring | Municipal Assembly |  | x | x |  |  | 12000 |  |  | x | HR | INTERNAL AUDIT
55 | Management & Administration | Human Resource Management | Prepare 2 NO. staff Promotion register | Municipal Assembly | x | x | x | x |  | 121000 |  |  | x | HR | ALL DEPARTMENTAL HEADS
56 | Management & Administration | Human Resource Management | Prepare and Submit Quarterly & Annual Capacity Building Reports | Municipal Assembly | x | x | x | x |  | 80900 |  |  | x | HR | ADMIN
57 | Management & Administration | Planning, Budgeting, Monitoring and Evaluation | Undertake stakeholder consultations on 2026 fee fixing resolution | Municipal Assembly | x | x | x | x | 15000 | 15000 |  |  | x | Budget | FINANCE
58 | Management & Administration | Planning, Budgeting, Monitoring and Evaluation | Organise 4No. budget committee meeting | Municipal Assembly | x | x | x | x |  | 20000 |  |  | x | Budget | PLANNING
59 | Management & Administration | General administration | Organise entity tender committee and tender opening meetings | Municipal Assembly | x | x | x | x |  | 15900 |  |  | x | Procurement | ADMIN
60 | Management & Administration | General administration | Organise procurement plan review meetings and quarterly update of plan | Municipal Assembly | x | x | x | x |  | 2650 |  |  | x | Procurement | PLANNING, BUDGET
61 | Management & Administration | General administration | Procurement of office equipment’s and consumables | Municipal Assembly | x | x | x | x |  | 32270.07 |  |  | x | Procurement | ADMIN
62 | Management & Administration | General Administration | Procurement/ Maintenance of Sanitary Tools and Equipment | Municipal Assembly | x | x | x | x |  | 418200 |  |  | x | Procurement | EHU,
63 | Management & Administration | General Administration | Procuring and updating of anti-virus | Municipal Assembly | x | x | x | x |  | 11000 |  |  | x | Procurement | MIS
64 | Management & Administration | General Administration | Update of Assembly’s social media platforms | Municipal Assembly | x | x | x | x |  | 5000 |  |  | x | MIS | ISD
65 | Management & Administration | General Administration | Maintenance and servicing of IT equipment / back-up of Assembly database | Municipal Assembly | x | x | x | x |  | 30000 |  |  | x | MIS | ADMIN
66 | Management & Administration | General Administration | Printing of bills for BOP &Property rate and bulk messaging | Municipal Assembly | x | x | x | x |  | 25000 |  |  | x | MIS | FINANCE, BUDGET, AUDIT, STATS
67 | Management & Administration | Planning, Budgeting, Monitoring and Evaluation | Organise town hall meetings and MMDCEs community engagement to sensitise community members on government flagship programmes | Nungua | x | x | x | x |  | 50000 |  |  | x | Development planning | ADMIN, BUDGET
68 | Management & Administration | Planning, Budgeting, Monitoring and Evaluation | Organise 1D1F, LED ,MPCU committee and monitoring and evaluation meetings | Nungua | x | x | x | x |  | 50000 |  |  | x | Development planning | AGRIC, SWCD
69 | Management & Administration | Planning, Budgeting, Monitoring and Evaluation | Undertake activities in preparation of the Assembly’s MTDP (2026-2029) | Nungua | x | x | x | x |  | 80000 |  |  | x | Development planning
70 | Social service delivery |  | Prepare environment safeguards and EPA permits | Municipal Assembly | x | x | x | x |  | 5000 |  |  | x | Development planning | ENV’T HEALTH
71 | Management & Administration | General Administration | Organise public education on a the 1992 constitution of Ghana for youth groups |  | x | x | x | x |  | 8000 |  |  | x | NCCE | ADMIN
72 | Management & Administration | General Administration | Organise Education on the sustainable management of the environment |  |  | x |  |  |  | 6000 |  |  | x | NCCE | EPA
73 | Management & Administration | General Administration | Organise education on human rights with special reference to children’s Right and child protection for faith based organizations and schools |  | x | x | x |  |  | 10000 |  |  | x | NCCE | LEKMA COURT
74 | Management & Administration | General Administration | Organise education on the need to pay taxes and rates for youth groups, church and mosques | Municipal wide | x | x | x | x |  | 10000 |  |  | x | NCCE | Revenue office
75 | Management & Administration | General Administration | Organize education on accountability (social auditing ) for faith based organisations and communities | Municipal wide |  | x | x |  |  | 8000 |  |  | x | NCCE | BUDGET
76 | Management & Administration | General Administration | Organised education on the restoration of the Ghanaian identity and values for faith based organization, schools, and groups | Municipal wide |  | X |  |  |  | 2000 |  |  | x | NCCE | ADMIN
77 | Management & Administration | General Administration | Constitution week celebration and quiz 2025 | Municipal wide |  |  | X |  |  | 8000 |  |  | x | NCCE | ADMIN
78 | Management & Administration | General Administration | Organise Public education on sanitation and proper disposal of refuse | Municipal wide | x | x | x | x |  | 4800 |  |  | x | NCCE | ENVIRONMENTAL HEALTH
79 | Management & Administration | General Administration | Undertake Establishment of Civic Education Clubs in Public and Private Schools | Municipal wide | x | x | x | x |  | 10000 |  |  | x | NCCE | ADMIN
80 | Management & Administration | General Administration | Radio programmes | Municipal wide | x | x | x | x |  | 4000 |  |  | x | NCCE | ISD
81 | Social service delivery | Education, Youth and Sports | Organize my FIRST DAY AT SCHOOL for all P1 and KG1s in the municipality. | Municipal wide | x | x | x | x |  | 20000 |  |  | x | Education Directorate | GES
82 | Social service delivery | Education, Youth and Sports | Organize best Teacher Prize in the Municipality | Municipal wide | x | x | x | x |  | 18000 |  |  | x | Education Directorate | GES
83 | Social service delivery | Education, Youth and Sports | Organize S.T.M.I.E Clinics. | Municipal wide | x | x | x | x |  | 22000 |  |  | x | Education Directorate | GES, ADMIN
84 | Social service delivery | Education, Youth and Sports | Organize inter – milo Under 13 boys soccer and netballs girls AND Under 15 girls soccer, volley ball, table tennis ball, hand ball and athletic competition. | Nungua | x | x | x | x |  | 20000 |  |  | x | Education Directorate | GES, ADMIN
85 | Social service delivery | Education, Youth and Sports | Organize Mock Exams for JHS 3 Pupils within the Municipality | Municipal wide | x | x | x | x |  | 35000 |  |  | x | Education Directorate | GES, ADMIN
86 | Social service delivery | Education, Youth and Sports | Organize girls and Boys club fair in both private and public 1st and 2nd Cycle Schools. | Municipal wide | x | x | x | x |  | 8000 |  |  | x | Education Directorate | GES, SWCD
87 | Social service delivery | Education, Youth and Sports | Organize Capacity workshop for Management, Staff, head teachers and teachers. | Municipal Assembly | x | x | x | x |  | 30000 |  |  | x | Education Directorate | GES, ADMIN
88 | Social service delivery | Education, Youth and Sports | Organize Career Guidance and Counselling on school selection and sensitization programmes for JHS 3 Students. | Municipal wide | x | x | x | x |  | 20500 |  |  | x | Education Directorate | GES, SWCD, GHS
89 | Social service delivery | Education, Youth and Sports | Conduct regular school inspection, monitoring and evaluation of educational delivery programmes in schools. | Municipal wide | x | x | x | x |  | 25000 |  |  | x | Education Directorate | GES, PLANNING
90 | Social service delivery | Education, Youth and Sports | Organize Municipal Education Sector and annual education staff performance Review meetings. | Municipal Assembly | x | x | x | x |  | 12000 |  |  | x | Education Directorate | GES, ADMIN
91 | Social service delivery | Education, Youth and Sports | Monitoring of BECE and WASSCE in the Municipality | Municipal wide |  | x |  | X |  | 20000 |  |  | x | Education Directorate | GES, ADMIN
92 | Social service delivery | Education, Youth and Sports | Organize Independence Day celebration for KG, 7Basic and 2nd Cycle Schools Pupils in the Municipality. | Nungua | x | x | x | x |  | 10000 |  |  | x | Education Directorate | GES, ADMIN
93 | Social service delivery | Education, Youth and Sports | Carryout Annual School Census | Municipal wide |  | x |  | x |  | 7000 |  |  | x | Education Directorate | STATISTICS
94 | Social service delivery | Education, Youth and Sports | Participate in Conference of Directors of Education. (CODE) | Nungua | x | x | x | x |  | 8000 |  |  | x | Education Directorate | GES, ADMIN
95 | Social service delivery | Education, Youth and Sports | Organise literacy classes and remedial classes for JHS/SHSGraduates | Municipal Wide |  |  | x | x |  | 1000 |  |  | x | NFED | GES
96 | Social service delivery | Education, Youth and Sports | Training of literacy facilitators | Municipal Wide | x | x |  |  |  | 2000 |  |  | x | NFED | GES
97 | Social service delivery | Education, Youth and Sports | Monitoring of literacy classes | Municipal Wide |  |  | x |  |  | 1000 |  |  | x | NFED | PLANNING
98 | Social service delivery | Education, Youth and Sports | Organize occupational skills development(OSD) and community outreach program and orientation | Municipal Assembly | x | x | x | x |  | 8000 |  |  | x | NFED | GES
99 | Social service delivery | Education, Youth and Sports | Municipal Literacy Day celebration | Municipal wide | x | x | x | x |  | 5000 |  |  | x | NFED | GES
100 | Social service delivery | Education, Youth and Sports | Graduation of learners | Municipal wide | x | x |  |  |  | 10000 |  |  | x | NFED | GES
101 | Social service delivery | Health Delivery | Organise 2nd quarter and 4th quarter routine immunization and vitamin A mop up for children under 5yrs. | Nungua |  | x |  | x |  | 15000 |  |  | x | Health | EU
102 | Social service delivery | Health Delivery | Organize quarterly , half a yearly reviews | Municipal Assembly | x | x | x | x |  | 8000 |  |  | x | Health | ADMINISTRATION
103 | Social service delivery | Health Delivery | Organize 8 financial and data validation workshop | Municipal Assembly | x | x | x | x |  | 13600 |  |  | x | Health | ADMINISTRATION
104 | Social service delivery | Health Delivery | Undertake Annual Community Health Volunteer Day & Health Screening | Municipal Assembly | x | x | x | x |  | 15000 |  |  | x | Health | ADMINISTRATION
105 | Social service delivery | Health Delivery | Undertake monthly validation and report on DHIMS. | Municipal Assembly | x | x | x | x |  | 12000 |  |  | x | Health | ADMINISTRATION
106 | Social service delivery | Health Delivery | Canopy project with medical equipments | Municipal wide | x | x | x | x |  | 48000 |  |  | x | Health | ADMINISTRATION
107 | Social service delivery | Health Delivery | Organize health day sensitisations and screenings - TB /HIV Aids malaria new born jaundice, cholera health breast feeding breast cancer etc.. | Municipal Assembly | x | x | x | x |  | 25000 |  |  | x | Health | ADMINISTRATION
108 | Social service delivery | Health Delivery | Acquire haematology analyser | Health center | x | x | x | x | 70000 |  |  |  | x | Health | ADMINISTRATION
109 | Social service delivery | Health Delivery | Organise monitoring and supervision and training on logistics management | Health center community wellness clinic | x | x | x | x |  | 14000 |  |  |  | Health | ADMINISTRATION
110 | Social service delivery | Health Delivery | To construct directly observed treatment (DOT) Unit at health center | Cluster of clinic | [5 empty] | 20000 |  |  |  | Health | ADMINISTRATION
111 | Social service delivery | Health Delivery | Undertake renovation of adolescent health corner- school clinic | [5 empty] | 40000 |  |  |  |  | Health | ADMINISTRATION
112 | Social service delivery | Trade, Tourism and industrial Development | Organise Bead making training for 50 youth in the municipality | Nungua |  | X |  | x |  | 4000 |  |  | x | Culture | SWCD,DEPT. OF COPERATIVES AND OTYHE
113 | Social service delivery | Trade, Tourism and industrial Development | Organise Kromafest for basic schools in the municipality/Cultural festivals | Nungua |  | x | X |  |  | 6000 |  |  | x | Culture | SWCD, DEPT. OF COOPERATIVES A D OTHERS
114 | Social service delivery | Trade, Tourism and industrial Development | Participate in Sankofa Drama festival(EBO WHYITE SHS DRAMA festival for second cycle schools. | Nungua |  |  |  | X |  | 3500 |  |  | x | Culture | EDUCATION
115 | Social service delivery | Trade, Tourism and industrial Development | Participate in Adesa Village (folksongs and storey telling competition) in Greater Accra | Municipal wide |  | x | x |  | 4000 | 4000 |  |  | x | Culture | TRADE AND INDUSTRY
116 | Social service delivery | Trade, Tourism and industrial Development | Participate in Kpatashie a cooking competition for all the 32 markets in Greater Accra Region. | Municipal Assembly |  |  |  | x |  | 4000 |  |  | x | Culture | ADMIN
117 | Social service delivery | Social welfare and community development | Train and Support PWDs with capital, equipment, medical bills and school fees | Municipal wide | x | x | x | x | 184416.05 |  |  |  | x | SWCD | ADMIN
118 | Social service delivery | Social welfare and community development | Reintegrate Abandoned & Missing / Found Children Into Families And Communities | Municipal Assembly |  |  | x |  |  | 2000 |  |  | x | SWCD | DPS, DOVSU
119 | Social service delivery | Social welfare and community development | Organise Mass education on teenage pregnancy, drug abuse, child marriage and maintenance during menstruation | Municipal wide | x | x | x | x | 10000 |  |  |  | x | SWCD | ADMINISTRATION
120 | Social service delivery | Social welfare and community development | Organize Case work sittings (Maintenance, family welfare, custody and paternity ) | Municipal Assembly |  | x | x |  | 1500 | 1500 |  |  | x | SWCD | ADMIN
121 | Social service delivery | Social Welfare and Community Development | Provide support and funding for Disability Programmes. (International Day of Persons with Disabilities). | Municipal Assembly |  | x |  | x | 6000 |  |  |  | x | SWCD | ADMIN
122 | Social service delivery | Social Welfare and Community Development | Registered the vulnerable on free NHIS | Municipal Assembly | x | x | x |  |  | 3000 |  |  | x | SWCD | NHIA
123 | Social service delivery | Social Welfare and Community Development | Monitor LEAP payment to household beneficiaries bi-monthly | Municipal Assembly | x | x | x | x |  | 1500 |  |  | x | SWCD | ADMIN
124 | Social service delivery | Social Welfare and Community Development | Sensitization of Community members on health, economic, social and government policies | Municipal wide | x | x | x | x | 6000 | GoG |  |  | x | SWCD | HEALTH
125 | Social service delivery | Social Welfare and Community Development | Monitoring of day care centres | Municipal wide | x | x | x | x |  | 1500 |  |  | x | SWCD | EDU
126 | Social service delivery | Social Welfare and Community Development | Inspect and supervise residential homes fro children | Municipal wide | x | x | x | x |  | 1500 |  |  | x | SWCD | ADMIN
127 | Social service delivery | Social Welfare and Community Development | Celebration of world day against child labour and the aged | Municipal wide |  |  | x |  |  | 4439 |  |  | x | SWCD | ADMIN
128 | Economic development | Social welfare and community development | Organize 1 workshop on small scale income generation activities | Municipal wide |  |  | x |  |  | 10000 |  |  | x | SWCD | CULTURE ,
129 | Economic development | Planning Budgeting and Statistics | Build, maintain and update the Municipal Business Register. | Municipal wide |  | x |  | x |  | 4500 |  |  | x | Statistics | BUDGET, FINANCE
130 | Economic development | Trade, Tourism and industrial Development | Undertake Audit inspection of cooperatives account | Municipal wide | x | x | x | x |  | 3500 |  |  | x | Department of C-operatives
131 | Economic development | Trade, Tourism and industrial Development | Train at least five cooperative groups to develop skills | Municipal wide |  | x | x |  |  | 10000 |  |  | x | Department of Co-operatives
132 | Economic development | Trade, Tourism and industrial Development | organise 4 community sensitisation program with SMEs on principles and benefits of forming cooperative groups and enrol them unto the group | Municipality wide | x | x | x | x |  | 6000 |  |  |  | Department of Co-operativses | CENTRAL ADMIN, AGRIC DIRECTORATE
133 | Economic development | Trade, Tourism and industrial Development | Register at least four (4) Co-operative Societies of SMEs and agricultural based businesses | Municipal wide |  | x | x |  |  | 2000 |  |  | x | Department of Co-operatives | CENTRAL ADMIN,
134 | Economic development | Trade, Tourism and industrial Development | Monitoring the work and progress of all newly formed Co-operative groups and a newly registered Co-operatives and Credit Unions. | Municipal wide |  |  | x |  |  | 2000 |  |  | x | Department of Co-operatives
135 | Economic development | Agricultural Services and Management | Collect data on market information to promote improved distribution of food stuff | Sookpoti |  | x |  |  |  | 1000 |  |  | x | AGRIC | STATISTICS
136 | Economic development | Agricultural Services and Management | Distribution of seedlings to farmers for PERD/PFJ | Municipal wide |  | x |  |  | 7000 |  |  |  | x | AGRIC | ADMIN
137 | Economic development | Agricultural Services and Management | Organize 1 farmers field day to demonstrate home gardening | Municipal Assembly | x |  |  |  | 9000 | 2,000,00 |  |  | x | AGRIC | ADMIN
138 | Economic development | Agricultural Services and Management | Training on credit in kind initiative for farmers | Municipal wide |  | x |  |  | 9000 |  |  |  | x | AGRIC | ADMIN
139 | Economic development | Agricultural Services and Management | Maintenance of vehicle and motorbike for AEAs | Municipal Assembly | x | x | x | x |  | 7500 |  |  | x | AGRIC | ADMIN
140 | Economic development | Agricultural Services and Management | Organise National Farmers and Fishermen Day Celebration | Nungua |  |  |  | x | 80000 |  |  |  | x | AGRIC | ADMIN
141 | Economic development | Agricultural Services and Management | Monthly monitoring and supervision on PFJ, PERD, GFJ, FWA | Municipal wide | x | x | x | x | 5000 | 5000 |  |  | x | AGRIC | ADMIN
142 | Economic development | Agricultural Services and Management | Organise 12 monthly staff meetings to discuss operations of the department | Municipal Assembly | x | x | x | x | 4000 | 4000 |  |  | x | AGRIC | ADMIN
143 | Economic development | Agricultural Services and Management | Undertake home and farm visits to reach actors along the agricultural value chain with improved technologies | Municipal wide |  |  | x |  | 10000 | 24060 |  |  | x | AGRIC | PLANNING
144 | Economic development | Agricultural Services and Management | Carry out anti-rabies campaign and vaccination for pets (dogs, cats and monkeys) | Municipal wide |  |  | x |  |  | 5000 |  |  | x | AGRIC | ADMIN
145 | Economic development | Agricultural Services and Management | Organise 7 days livestock bazaars( livestock harvest) for men and women farmers | Nungua |  |  | x |  | 1000 | 4000 |  |  | x | AGRIC | ADMIN
146 | Economic development | Agricultural Services and Management | Train women and youth farmers on climate smart agriculture to mitigate the effects of climate change | Municipal wide |  |  | x |  | 1000 | 2500 |  |  | x | AGRIC | ADMIN
147 | Economic development | Agricultural Services and Management | Train farmers on improved technologies(post-harvest, soil water management, GAPs, disease identification, prevention, intensifying surveillance, control and HIV/AIDS | Municipal Wide |  | x |  |  | 5000 |  |  | X |  | AGRIC | MHD, RDA